## Action Plan
Day of Action Key dates
Day | Status | Due Date | What | Notes
Earth Day | Done | 2020-04-22 | Announce Day of Action idea. Engage with external community to gather contributor requirements | Light announcement, but because there is a delay engaging with NROs, so no major push just yet
World Environment Day | To Do | 2020-06-05 | Day of Action pilot (NROs + existing relationship, Red Hat). | CANCELLED!
World Cleanup Day | To Do | 2020-09-19 | Day of Action PILOT. Bug Hunt
Earth Day | To Do | 2021-04-22 | Much bigger Day of Action
Action Plan
Management
| Working | 2020-07-29 | Reach out to the community - what would they like to see in the day / how would they like to contribute?
| To Do | 2020-08-07 | Ask each NRO to communicate with their volunteers. Could specific NROs "sponsor" certain tasks, and be on hand to help it get done? (Would provide a mix of internal knowledge and external expertise) Ask our friends and networks to turn up. Reach out to other NGOs. Talk about it in places NGOs are. Use the internal network people have | Need to do a stakeholder call; see how they feel about the whole thing, suzi + Luca and the senior admin group
| Done | 2020-05-29 | Agree channels that will be used by internal and external contributors | Community 2020 Matrix
| Done | 2020-05-29 | Agree resources and channels to keep managing the community. Maybe another NGO would want to lead something similar and could keep engagement going. Agree the frequency for meetings and places to join with the contributors (perhaps every one or two months) | Community 2020 Matrix
| Done | 2020-05-29 | Agree that We Are Open are the 'Open Strategists', who own the initiative and can assign team tasks and ensure team know how to facilitate relationship and manage the contributions | Should WAO no longer be in this position, GPI will need to replace WAO with a new owner for the initiative
| Done | 2020-05-29 | Assign roles for individuals to oversee key work | theme owners
| Done | 2020-05-29 | Agree to allocate 20-30% of the team's time to prepare to manage contributions to and ongoing contributor relationships following the DofA. Have time set aside to follow up on tasks from the DoA and respond to contributors questions.
| To Do | 2020-08-28 | Identify missing documentation (see suggested task tab) | Need team input
| To Do | 2020-08-28 | Check the DofA and key dates don't clash with something eg certificates expiry. If they do, agree mitigation
| Working | 2020-08-28 | Create a Communications Plan to promote Day of Action and let contributors know key dates. Ensure contributors know how they can continue to stay in touch and contribute. Be clear about the opportunities, channels for discussion | Day of Action strategy doc has a comms roadmap, DoA slides have the narrative, Community Matrix needs to be translated to handbook
| Working | 2020-08-28 | Ensure tools and resources contributors will need are in place e.g. the Design System. (Aiming for end of quarter 3); Provide accurate clean data from the GP website in a broader context, eg not just from P4, to test; Provide Data standards to be able to analyse properly
| Working | 2020-08-28 | Create a system for allocating tasks and checking level of expertise and on what basis contributors wish to contribute. Provide means for them to submit portfolio or previous work | Ties in with work Walter is doing on processes and task management
Task Prep - Pilot
| To Do | 2020-06-12 | Agree and refine tasks in Suggested Tasks / Requirements sheet. Complete column: Context / data / documentation required | Walter's change backlog
| To Do | 2020-06-12 | Based on above, agree documentation that needs to be updated in Document Sprint
| Done | 2020-06-12 | Create a clear brief for each task, including: length of task and timeline; clear objectives; provide a taster/example if possible; dependencies on other work; clear labelling, level of difficulty, where to access documentation, tools and help needed | Need a template
Pilot
World Environment Day | Team Decision | 2020-06-05 | Team be on hand to facilitate contributions, answer queries, provide help etc | Need a new date
| To Do | 2020-08-28 | Use lessons learnt to feed into task development for Day of Action
Day of Action Task Prep
| To Do | 2020-07-31 | Agree and refine tasks in Suggested Tasks / Requirements sheet. Complete columns: Part of a sprint cycle?, Mid-cycle? (don't assign tasks that are mid-cycle), Level, Relationship with contributor, Context / data / docs required, Timeline, Priority | Need label for complexity, Ask Walter/Lilian about labeling system
| To Do | 2020-07-31 | Select tasks that have been allocated HIGH priority as core tasks. Include tasks that require low expertise, eg testing on multiple different devices at the same time. (Could be done if the pages being tested automatically recorded the device and browser profile) | Tasks related to Product vs Project
| To Do | 2020-08-28 | Create a clear brief for each task, including: length of task and timeline; clear objectives; provide a taster/example if possible; dependencies on other work; clear labelling, level of difficulty, where to access documentation, tools and help needed | exists in Github
| To Do | 2020-08-28 | Ensure backlog tickets are clearly defined so people can work on them autonomously and know where to go for questions / decisions
| To Do | 2020-09-18 | Self select / Allocate tasks
Day of Action
World Cleanup Day | To Do | 2020-09-19 | Team be on hand to facilitate contributions, answer queries, provide help etc
Follow Up
| To Do | 2020-09-21 | Give out: Physical and digital swag, eg t-shirts, digital badges Doughnuts
| To Do | 2020-09-21 | Use the Communications Plan to point contributors to how they can continue to stay in touch and contribute. Work with other stakeholders need to lead the conversation. Focus on a longer term relationships. Keep providing opportunities, the space and topics for discussion
Much bigger Day of Action
Earth Day | To Do | 2021-03-31 | Refine tasks and requirements for bigger Day of Action, based on lessons learnt from Day of Action
| To Do | 2021-04-21 | Allocate tasks
| To Do | 2021-04-22 | Team be on hand to facilitate contributions, answer queries, provide help etc
Follow Up
| To Do | 2021-04-23 | Give out: Physical and digital swag, eg t-shirts, digital badges Doughnuts
| To Do | 2021-04-23 | Use the Communications Plan to point contributors to how they can continue to stay in touch and contribute. Work with other stakeholders need to lead the conversation. Focus on a longer term relationships. Keep providing opportunities, the space and topics for discussion | Community 2020 Matrix
| To Do | 2021-04-23 | Refine tasks and requirements for bigger Day of Action, based on lessons learnt

## General Prep
Preparation - based on GP INTERNAL stakeholder responses
As a contributor, I need | As a member of GP team, I need | Good ideas | Theme owners ideas
For everything to be in place for me to contribute effectively | To have the right channels and documentation in place, and people know where to go and what channels to use. A project manager to assign tasks, someone overall in charge. Assign roles for individuals to oversee key work. Contingency - ensure people are allocated 20-30% of their time to deal with it | We need a design process put in place - so that others can easily follow | Ensure everyone has their eyes on the system Make sure it doesn’t clash with something: eg certificates expiry Any updates that are scheduled to run
To understand how I can contribute. Guidance where to look to in order to contribute | Reach out to the community - what would they like to see in the day / how would they like to contribute? Each NRO can communicate with their volunteers. Ask our friends and networks to turn up, just in case so we have people that we can rely on to turn up Reach out to other NGOs. Talk about it in places NGOs are. Use the internal network people have | Come up with a number of task ideas and put them to the community. "There is tension between the old world of P3 (website) and the new world of P4 (engagement) - people are looking for P3 things inside P4" | Very good storytelling both internally and externally Make sure the objectives are clear, provide a bit of a taster Reach out to the community - what would they like to see in the day / how would they like to contribute? Each NRO can communicate with their volunteers Ask our friends and networks to turn up, just in case so we have people that we can rely on to turn up Reach out to other NGOs
To be able to contribute effectively. Know how to use my expertise to contribute | To provide a clear brief, including length of task and timeline; clear objectives; a taster; dependencies on other work; clear labelling for tasks, define level of difficulty |  | Make sure brief is clear and expectations are managed Align the comms Get the basis rights
To be able to contribute without interuption | To ensure everyone has their eyes on the system Make sure the DofA and key dates don't clash with something eg certificates expiry Any updates that are scheduled to run. To help the DofA be a great experience, make a good impression |  | Ensuring we have the right channels and documentation, and people know where to go and what channels to use
Design documentation | To ensure that the tools are in place that contributors might need e.g. the design system needs to be in place. Aim to have design system hopefully by end of quarter 3 | We need to wait until the new Brand messaging is complete before creating UI tasks | Pre-write messages Keep an eye
To know how to open a pull request - feel familiar with P4 | To ensure backlog tickets are clearly defined so people can work on them autonomously and know where to go for questions / decisions |  | We need to know our participants in advance to pitch at right level and manage expectations. Reach out to external stakeholders, especially other NGOs. Have interaction with them rather than the Day of Action being the first day we interact with them
To know that my contribution will make a difference | Don’t give work that is mid-cycle |  | We must always write a brief and this must include how long it should take and when it needs to be delivered by If it’s dependent on any other pieces of work in another piece of work that hasn’t been done Don’t give work that is mid-cycle Have a project manager to assign tasks, someone overall in charge Assign roles for individuals to oversee key work Contingency - ensure people are allocated 20-30% of someone’s time to deal with it
To have a variety of ways to contribute - ranging from doing testing to complex code contributions. Know where I fit in | Know our participants in advance to pitch at right level and manage expectations. Reach out to external stakeholders, especially other NGOs. Have interaction with them rather than the Day of Action being the first day we interact with them |  | We must ensure that the tools are in place that contributors might need e.g. the design system needs to be in place. Starting it now. Getting rules in place eg This will be impacted by the new branding (affects UI). Won’t do this until that has been finalised Accessibility (affects colour etc) reviewing the blocks to ensure they’re doing what they want them to do UX affects how everything works together Aim to have design system hopefully by end of quarter 3, depending on time Magali has
To know that I can contribute even if I'm unsure of my digital knowledge and skills. As a non-techie, I want a task where I dont need to be an expert (e.g. I could do testing on my device) | To create tasks that require low expertise, eg testing on multiple different devices at the same time. (Could be done if the pages being tested automatically recorded the device and browser profile) |  | Need to see portfolio or previous work
Plenty of notice and reminders about what's happening | To create a communications plan about key dates |  | Would need to give a non-mission critical task first to check how much you could rely on them
Resources made available to do analysis on | To ensure that the tools are in place that contributors might need. Provide accurate clean data from the GP website in a broader context, eg not just from P4, to test. Provide Data standards to be able to analyse properly |  | Need clear facilitation to manage the contributions Break out into different sessions, different people speaking, effective facilitation techniques
To have access to GP personnel to answer questions / help me contribute effectively | To have time set aside to follow up on tasks from the DoA and respond to contributors questions. Need clear facilitation to manage the contributions Break out into different sessions, different people speaking, effective facilitation techniques. -Could specific NROs "sponsor" certain tasks, and be on hand to help it get done? That way there is a mix of internal knowledge and external expertise? |  | Give out: Physical and digital swag, eg t-shirts, digital badges Doughnuts Talking about it in places NGOs are Using the internal network people have
To know if I can contribute in a consultancy capacity | Need to see portfolio or previous work. Would need to give a non-mission critical task first to check how much you could rely on them |  | DoA needs to be a great experience, make a good impression Resources to keep managing the community Maybe another NGO would want to lead something similar and could keep engagement going Frequent meetings and places to join with the contributors, every one or two months Other stakeholders need to lead the conversation with us Focus on a longer term relationship: Keep providing opportunities, the space and topics for discussion
Follow up
Recognition (swag) - both physical and digital eg t-shirts, digital badges | Give out: Physical and digital swag, eg t-shirts, digital badges Doughnuts
To know I can continue the relationship and learn how my contribution has help P4 | Resources to keep managing the community. Maybe another NGO would want to lead something similar and could keep engagement going. Frequent meetings and places to join with the contributors, every one or two months. Other stakeholders need to lead the conversation with us. Focus on a longer term relationship: Keep providing opportunities, the space and topics for discussion

## Suggested Tasks Requirements
Tasks / Requirements for Contributions suggested by INTERNAL stakeholders
NOTES: Priority / level etc set to show how sheet works. Selecting High priority, will highlight task in green
Tasks | Requirements | Context / data / docs required | Labels (refer to https://github.com/greenpeace/planet4/labels) | Part of a sprint cycle? | Mid-cycle? | Level | Relationship with contributor | Timeline | Priority | Theme owner suggestions
Development
Technical documentation | Identify gaps in technical documentation and translate into tasks |  | Documentation, dev | [5 empty] | High | Gaps in technical documentation
Facilitated conversations on topics | Define topics where external expertise would be valuable and define tasks |  |  | Yes | No |  |  |  | Low | Some of the tasks could be facilitated conversations that allow external participants to share their expertise around a particular topic.
Refactoring code | [8 empty] | Low | Refactoring code (low priority)
Moving contribution backlog to Github | [8 empty] | Low | Help move the contribution backlog to Github?
Design | Easy task to begin with - but that leads to ongoing relationship with contributor
UX and UI tasks | Must have new GP branding in place before creating these tasks |  |  |  |  | Easy |  | June onwards |  | Lots of UX and UI tasks
User research | [5 empty] | Easy |  |  |  | User Research - Interviews with stakeholders, surveys with the community, user flows, wireframes, directions, creating a prototype
Interviews with stakeholders | [5 empty] | Moderate
Surveys | [5 empty] | Moderate
User flows | [5 empty] | Difficult
Wireframes | Must have new GP branding in place before creating these tasks |  |  |  |  | Difficult |  | June onwards
Directions | Define tasks |  |  |  |  | Moderate
Create a prototype | Must have new GP branding in place before creating these tasks |  |  |  |  | Difficult |  | June onwards
General
Design DoA T-shirt | Formatting requirements; must-includes | [6 empty] | Pre-conversation |  | Have pre-conversations with the external community to get help designing the DoA T-shirt!
Test on multiple devices | Ensure pages to be tested can record device and browser profile | [8 empty] | Testing on multiple different devices at the same time could be done if the pages being tested automatically recorded the device and browser profile
Take visual notes of your contribution to the DoA | Suggestions / guidance on how to take visual notes | [8 empty] | Capture openly, eg take a visual note of everything you are doing during the Day of Action, make noise, share with your network
Share your contribution with your network | Suggestions / guidance on sharing your work openly | [8 empty] | Capture openly, eg take a visual note of everything you are doing during the Day of Action, make noise, share with your network
Help us tell the story | Suggestions / guidance on storytelling | [8 empty] | Creating narrative around tech
Data Analysis
Data standards analysis | Data standards need to be in place to provide starting point | [8 empty] | Data standards to analyse
Ideas for testing / what to test | Get ready-to-test ideas from external analysts | [8 empty] | Ideas re testing and what we could start testing
Data visualiation / storytelling for data | Data to visualise, tell a story about | [8 empty] | Data visualisation and storytelling for data
Knowledge share | Platform for knowledge sharing - link to community strategy platforms | [8 empty] | Be part of knowledge share
Good practice guidance for integrating data across different platforms | Template for guidelines | [8 empty] | How to integrate data through different platforms, eg contributing to good practice guidelines
Good practice guidance for global user research and knowledge sharing | Template for guidelines | [8 empty] | User research and sharing experience re how we do that for a global product, eg how we manage this across cultures, timezones, differing needs
Missing Documentation
https://planet4.greenpeace.org/blocks/ | Add a live example of each block
Demo page on the handbook | all the blocks on one page
Elastic search documentation

## Requested Tasks
Tasks EXTERNAL contributors said they could do
NOTES: Priority / level etc set to show how sheet works. Selecting High priority, will highlight task in green
Responses | Tasks | Requirements | Part of a sprint cycle? | Priority | Level | Relationship with contributor | Context / data / docs required | Timeline
EXTERNAL CONTRIBUTORS
8 | Kubernetes / New Relic / Infra Management
8 | Front end development
8 | Feature Testing / QA
8 | Open source and open development strategy
7 | PHP development
7 | User Testing / Prototype testing
7 | User guides / Technical documentation
5 | UX design
5 | UI / Web design
5 | A/B Testing / Optimisation
5 | Engagement strategy / features
4 | React Development
2 | SCRUM mentorship / Product dev practices
2 | Backend
1 | Localisation
1 | Other writing

## Marketing
Insights from EXTERNAL Contributors | Who | Wants | Marketing / Advice
External Contributors - respondents to survey
Motivations for external contributors in order | 17 | Listing as a contributor on a project page | Keep going! Lots of projects seem to get this far then give up.
AS OF 28/4/20 | 12 | Shout-out on social media (e.g. by a significant individual/organisation) | Good luck!
| 8 | Swag (e.g. t-shirts bags pins) | Developer Experience is **super** important for a successful Open Source project. Many of my favourite projects are big proponents of that, and they go as far saying they do "DDD" - Documentation Driven Development.
| 7 | Digital credential (e.g. certificate or badge which you can share to evidence your contribution) | A lot of Open Source projects are alienating many contributors because English speaking ppl (esp Americans) get much more recognition/attention/power compared to non-english speaking ppl. Since most communication in OS-projects happens in English, American culture/politics is very prominent in a lot of OS-communities (just one of many examples: the fight for equal rights by the LGTB-movement is currently a hot topic in the US, while it is much less prominent in Europe). Please make sure you value ppl for their input, not on the volume of their voice.
| 2 | Prizes (e.g. a bug bounty) | Stay away from (close) ties to proprietary platforms
| 1 | Social component | I like to do open source projects to learn a skill, to collaborate with friends or to feel like I am helping push forward a cause. I don't often give money to orgs but I will likely volunteer time or services.
| 1 | Improving something I'm using everyday | No
| 1 | Simply finding issues with the tech I have installed and then fixing and contributing back to the project | I don't think contributing is about peresonal recognition or rewards and I found a lot of the questions were leading in that direction. For me it's because of a passion, love, fanaticism and just the enjoyment of doing. Next comes the values, altruism, and community. But material rewards isn't something of interest.
| 1 | Being able to give back and help the project | DO NOT let identity politics enter into any aspect of the project or it WILL fail.
| 1 | Money | good luck! building community and being responsive is the key
| 1 | i wanted to learn | No thanks
| 1 | to help others solve problems
| 1 | A belief in the concept

## Personas
Insights from Internal & External Contributors | Who | Reason | Wants to | Need | Can | Marketing / Advice
Internal Contributors
Developer Stakeholders (NRO Contributors)
I'm empowered to open a pull request - I'm familiar with P4 | Developer Stakeholders (NRO Contributors) |  |  | To know how to open a pull request - feel familiar with P4
I can work on things that benefits our NRO | Developer Stakeholders (NRO Contributors) | I am paid by my employer to contribute | Work on something that benefits our NRO |  | Work on things that benefit our NRO
Time commitments of people in the team. Day of action helps because it has a specific date. Risk that people won’t make the time for it, and contributors ask questions and no one is there to answer. Someone opens a PR and it takes forever to be reviewed. People are not responsive. No immediacy. | Developer Stakeholders (NRO Contributors) |  |  | To have time set aside to follow up on tasks from the DoA and respond to contributors questions
Level of expertise is outside the P4 team. Deciding the scope...labeling important. | Developer Stakeholders (NRO Contributors) |  |  | To have clear labelling for tasks, defining level of difficulty
Even if we have a big backlog, some tickets might not be well defined and people can’t work autonomously. No decision makers available, distributed leadership. | Developer Stakeholders (NRO Contributors) |  |  | To ensure backlog tickets are clearly defined so people can work on autonomously and know where to go for questions / decisions
Opportunities - areas that we’re not ready for actual code, maybe we can still architecture this, engineer this. | Developer Stakeholders (NRO Contributors) | I am paid by my employer to contribute | Identify areas where we're not ready for code but would welcome input
We need DESIGN. Tech needs design documentation. Devs don’t know how something is supposed to look. Documentation isn’t tested. Needs: Design documentation. | Developer Stakeholders (NRO Contributors) |  |  | Design documentation
Designer Stakeholders (P4 web editors, Co-ordinators, Digital Campaigners)
I can provide guidance for external contribution (framing tasks) | Designer Stakeholders (P4 web editors, Co-ordinators, Digital Campaigners) |  |  |  | Provide guidance for external contribution (framing tasks)s
Our NRO has its own priorities | Designer Stakeholders (P4 web editors, Co-ordinators, Digital Campaigners) | I am paid by my employer to contribute | Know NRO's priorities so tasks can be aligned
I can contribute ideas and priorities to P4 community ideas push | Designer Stakeholders (P4 web editors, Co-ordinators, Digital Campaigners) | I am paid by my employer to contribute | Contribute ideas and priorities to the P4 Community ideas push
I can vote ideas up and down on the P4 Community ideas push | Designer Stakeholders (P4 web editors, Co-ordinators, Digital Campaigners) | I am paid by my employer to contribute | Vote ideas up and down on the P4 Community ideas push
I need plenty of notice and a reminder about what's happening. | Designer Stakeholders (P4 web editors, Co-ordinators, Digital Campaigners) |  |  | Plenty of notice and reminders about what's happening
Program Stakeholders (web admins, Editors, Digital Campaigners)
I have an unknown level of digital knowledge and skills | Program Stakeholders (web admins, Editors, Digital Campaigners) |  |  | To know that I can contribute even if I'm unsure of my digital knowledge and skills
I am well connected within our NRO (I wear many hats) | Program Stakeholders (web admins, Editors, Digital Campaigners) |  |  |  | Do a range of things and connect them across the NRO
My experience with P4 is variable - it may be just testing or might be a complex contribution | Program Stakeholders (web admins, Editors, Digital Campaigners) |  |  | To have a variety of ways to contribute - ranging from doing testing to complex code contributions
Analytics Tools Stakeholders (NRO Analysts, Insights team)
Some of us have more resources available to do Analysis than others. | Analytics Tools Stakeholders (NRO Analysts, Insights team) |  |  | Resources made available to do analysis on
We want Case studies, Training content, webinars, leadership | Analytics Tools Stakeholders (NRO Analysts, Insights team) | Experience | Have case studies, training content, webinars, leadership
We need accurate clean data from the website in a broader context, eg not just for P4, to test | Analytics Tools Stakeholders (NRO Analysts, Insights team) |  |  | Accurate clean data from the GP website in a broader context, eg not just from P4, to test
We need Data standards to be able to analyse properly | Analytics Tools Stakeholders (NRO Analysts, Insights team) |  |  | Data standards to be able to analyse properly
External Contributors
Developers
I'm aligned to GP and its mission | Developers | Recognition | Have recognition for fact that I am aligned to GP and its mission
I need guidance where to look | Developers |  |  | Guidance where to look to in order to contribute
I need to know where I fit in | Developers |  |  | Know where I fit in
I have expertise - how can I get to use it? | Developers |  |  | Know how to use my expertise to contribute
Is there a bug heap? | Developers | Fixing bugs | Know if there is a bug heap
I want to help improve this platform | Developers | Experience | Help improve this platform
Can I contribute in a consultancy capacity? | Developers |  |  | To know if I can contribute in a consultancy capacity
Designers (working in a corporate situation, front end designer, UI and UX, illustrators)
This might be a way into getting some work from GP | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Career | A way into getting some work from GP
I want to save the planet too | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Values | Save the planet
I want to share my knowledge and skills | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Experience | Share my knowledge and skills
I want to work on something interesting | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Creative outlet | Work on something interesting
I want to add/show off my style | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Recognition | To add / show off my style
I can bring fresh eyes to design | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Fixing bugs | Bring fresh eyes to the design
I can make things run smoother because of better design | Designers (working in a corporate situation, front end designer, UI and UX, illustrators) | Experience | Make things run smoother because of better design
General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4)
I am into Tech and saving the planet (more experienced at one than the other?) | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Values | Use tech and save the planet
I want to give something back | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Values | Give something back
I want to feel good about my contribution | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Values | Feel good about contributing
I want the opportunity to make something better | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Fixing bugs | Make something better
I want to become part of GP and the activism community | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Social side | Become part of GP and the activism community
I want to show what I can do | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Recognition | Show what I can do
I want to add this to my professional portfolio | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) | Career | Add this to my professional portfolio
I need a clear brief of how I can contribute | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) |  |  | A clear brief of how I can contribute
I need recognition (swag???) | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) |  |  | Recognition (swag) - both physical and digital eg t-shirts, digital badges
As a non-techie, I want a task where I dont need to be an expert (testing on my device?) | General (someone from another NGO, Volunteers, Developers, anyone who is interested in P4) |  |  | As a non-techie, I want a task where I dont need to be an expert (e.g. I could do testing on my device)
Data Analysts (possibly from other NGOs, or experts from corporate world)
I can share a lot about what methods we use in the industry | Data Analysts (possibly from other NGOs, or experts from corporate world) |  |  |  | Share a lot about what methods we use in the industry
We can share skills between NGOs | Data Analysts (possibly from other NGOs, or experts from corporate world) |  |  |  | Share skills between NGOs
I want to contribute to an open source project | Data Analysts (possibly from other NGOs, or experts from corporate world) | Scratching your own itch | Contribute to an open source project
I want to gain some recognition for contribution | Data Analysts (possibly from other NGOs, or experts from corporate world) | Recognition | Gain some recognition for contribution

## Pre-mortem Concerns & mitigatio
Pre-mortem Concerns & Mitigations
TL;DR | Concern | Raised by |  |  |  | Captured Mitigations
Tumbleweed | External Contributors didnt show | Development | Design | General | Data Analysts | Very good storytelling both internally and externally Make sure the objectives are clear, provide a bit of a taster Reach out to the community - what would they like to see in the day / how would they like to contribute? Each NRO can communicate with their volunteers Ask our friends and networks to turn up, just in case so we have people that we can rely on to turn up Reach out to other NGOs
Bad tasks | Our tickets arent in good shape / Brief wasn't clear / People didnt know what to do / Agenda is not clear | Development | Design | General | Data Analysts | Make sure brief is clear and expectations are managed Align the comms Get the basis rights
Lack of GP time invested | P4 time commitments - people dont make the time / We weren't able to manage them / didnt think it was their job | Development | Design | General |  | We must always write a brief and this must include how long it should take and when it needs to be delivered by If it’s dependent on any other pieces of work in another piece of work that hasn’t been done Don’t give work that is mid-cycle Have a project manager to assign tasks, someone overall in charge Assign roles for individuals to oversee key work Contingency - ensure people are allocated 20-30% of someone’s time to deal with it
Skills mismatch | Mismatch in skills required to complete task / Contributors are too different and people get frustrated as they want differing needs to be met / The level wasn’t right. A lot of people with different knowledge, so some people feel it isn’t high level enough. Or they might work with different types of data | Development | Design |  | Data Analysts | We need to know our participants in advance to pitch at right level and manage expectations. Reach out to external stakeholders, especially other NGOs. Have interaction with them rather than the Day of Action being the first day we interact with them
Runway to big | Local dev environment takes a long time to setup | Development
The world is too big | Time Zones got in the way | Development
Incomplete Docs | Documentation not complete | Development |  |  | Data Analysts | Ensuring we have the right channels and documentation, and people know where to go and what channels to use
They werent prepped | Participant wasn't prepared |  | Design
We didnt prep them | We didnt give them the right tools to be able to complete task |  | Design |  |  | We must ensure that the tools are in place that contributors might need e.g. the design system needs to be in place. Starting it now. Getting rules in place eg This will be impacted by the new branding (affects UI). Won’t do this until that has been finalised Accessibility (affects colour etc) reviewing the blocks to ensure they’re doing what they want them to do UX affects how everything works together Aim to have design system hopefully by end of quarter 3, depending on time Magali has
Not enough time | There wasn't enough time. |  | Design
Showboating illustrators | Showboating illustrators took it off brand |  | Design
Poor Contributions | Quality of contribution was low |  | Design |  |  | Need to see portfolio or previous work
Time mismatch | Contributions didnt fit with how we work (sprints!) |  | Design |  |  | Would need to give a non-mission critical task first to check how much you could rely on them
Security hack | The site got hacked with an unsavoury visual message |  |  | General |  | Ensure everyone has their eyes on the system Make sure it doesn’t clash with something: eg certificates expiry Any updates that are scheduled to run
Social Media bomb | We got hates on social media |  |  | General |  | Pre-write messages Keep an eye
Act of God | Our day was impacted by Corona |  |  | General
Resources fall over | The Website couldn't cope with all the activity |  |  | General
People dont stay | People get distracted - give up early |  |  |  | Data Analysts | Need clear facilitation to manage the contributions Break out into different sessions, different people speaking, effective facilitation techniques
No hook | People aren’t motivated to participate and we couldn’t reach the people we want to get. Couldn’t get NGOs involved |  |  |  | Data Analysts | Give out: Physical and digital swag, eg t-shirts, digital badges Doughnuts Talking about it in places NGOs are Using the internal network people have
Short term participation | People don’t apply the knowledge later, they’ve turned up for the day but then it doesn’t get followed up by GP to help people build on the relationship |  |  |  | Data Analysts | DoA needs to be a great experience, make a good impression Resources to keep managing the community Maybe another NGO would want to lead something similar and could keep engagement going Frequent meetings and places to join with the contributors, every one or two months Other stakeholders need to lead the conversation with us Focus on a longer term relationship: Keep providing opportunities, the space and topics for discussion
We don’t have the right channels and documentation

## Good ideas
Good ideas & other thoughts
Dev | Could specific NROs "sponsor" certain tasks, and be on hand to help it get done? That way there is a mix of internal knowledge and external expertise?
Design | Come up with a number of task ideas and put them to the community
We need a design process put in place - so that others can easily follow
We need to wait until the new Brand messaging is complete before creating UI tasks
There is tension between the old world of P3 (website) and the new world of P4 (engagement) - people are looking for P3 things inside P4
General | Testing on multiple different devices at the same time could be done if the pages being tested automatically recorded the device and browser profile

## External survey responses
Timestamp | How long have you been contributing to Open Source projects? | When you think of a successful Open Source project, is there one in particular that comes to mind? Why? | What would you say is the most important reason that you contribute to Open Source projects? | Have any of the following encouraged you to contribute to Open Source projects? | Please tick any of the following that you could potentially contribute to with the Planet 4 project: | How much time do you have to contribute? | Is there anything else you would like to tell us that would help shape the Planet 4 Open Source contribution program? | Name | Location
2020-04-14 13:21 | More than 3 years | Clear goals that are well communicated on an ongoing basis. | Values |  | Open Source and Open Development strategy, Engagement strategy / features | An hour or less a week | Keep going! Lots of projects seem to get this far then give up. |  | Europe
2020-04-14 14:56 | More than 3 years | WordPress - it has wretched governance but the way it’s a public end-user facing project continually brings in new contributors that a dev-facing project or something more niche like a Linux program rarely gets | Social side | Shout-out on social media (e.g. by a significant individual/organisation), Listing as a contributor on a project page | Front-End Development, PHP Development, React Development | An hour or less a week | Good luck! |  | North America
2020-04-14 19:30 | More than 3 years | Laravel and Ruby on Rails. They are my favourite examples because they are awesome open source projects, but the maintainers also have a related businesses that doesn't depend on the open source project to pay the bills. This is important because there may be sustainability issues or a conflict of interests otherwise (such as Open Core, etc.) | Values | Swag (e.g. t-shirts, bags, pins), Listing as a contributor on a project page, Improving something I'm using everyday | Front-End Development, PHP Development, React Development, SCRUM mentorship / Product dev practices, User guides / technical documentation | An hour or less a week | Developer Experience is **super** important for a successful Open Source project. Many of my favourite projects are big proponents of that, and they go as far saying they do "DDD" - Documentation Driven Development. | Noel De Martin | Europe
2020-04-15 09:57 | More than 3 years | Drupal | Recognition | Swag (e.g. t-shirts, bags, pins), Shout-out on social media (e.g. by a significant individual/organisation), Digital credential (e.g. certificate or badge which you can share to evidence your contribution), Listing as a contributor on a project page | PHP Development, Open Source and Open Development strategy, Feature Testing / QA, A/B Testing / Optimisation, User Testing / Prototype testing | < 5 hours p/week | A lot of Open Source projects are alienating many contributors because English speaking ppl (esp Americans) get much more recognition/attention/power compared to non-english speaking ppl. Since most communication in OS-projects happens in English, American culture/politics is very prominent in a lot of OS-communities (just one of many examples: the fight for equal rights by the LGTB-movement is currently a hot topic in the US, while it is much less prominent in Europe). Please make sure you value ppl for their input, not on the volume of their voice. |  | Europe
2020-04-15 10:03 | More than 3 years | Nextcloud. Backed by an independent company with a fully open source business model (no "open core"), which makes it possible to pay developers. | Social side | Digital credential (e.g. certificate or badge which you can share to evidence your contribution), Listing as a contributor on a project page, Social component: i received a lot of personal help when i made the first steps into foss, particularly Linux. | PHP Development | < 5 hours p/week | Stay away from (close) ties to proprietary platforms | Blizzz | Europe
2020-04-15 18:20 | More than 3 years | Community driven | Values | Swag (e.g. t-shirts, bags, pins), Listing as a contributor on a project page | Front-End Development, UX Design, UI / Web Design, Feature Testing / QA, A/B Testing / Optimisation, User Testing / Prototype testing | An hour or less a week |  |  | Europe
2020-04-16 14:40 | More than 3 years | p5.js - because there is a healthy combination of community led conversations and project/org specific ones. | Experience | Shout-out on social media (e.g. by a significant individual/organisation), Listing as a contributor on a project page | UX Design, UI / Web Design, Open Source and Open Development strategy, A/B Testing / Optimisation, User Testing / Prototype testing, User guides / technical documentation | An hour or less a week | I like to do open source projects to learn a skill, to collaborate with friends or to feel like I am helping push forward a cause. I don't often give money to orgs but I will likely volunteer time or services. | Jess Klein | North America
2020-04-16 17:11 | More than 3 years | WordPress | Values | Swag (e.g. t-shirts, bags, pins), Listing as a contributor on a project page | Feature Testing / QA, User guides / technical documentation | < 5 hours p/week | No | Stephen Downes | North America
2020-04-16 19:20 | More than 3 years | Linux - it's everywhere, it started small now probably the most used operating system, android built on it, most of the Internet is powered by it, and now Microsoft is adopting into its Windows operating system. It truly has dominated the tech world and is open source and free | Values | Simply finding issues with the tech I have installed and then fixing and contributing back to the project. No reward necessary. I've also found certain podcasts encouraging | PHP Development, Kubernetes / New Relic / Infra management, Open Source and Open Development strategy, Engagement strategy / features, SCRUM mentorship / Product dev practices | < 5 hours p/week | I don't think contributing is about peresonal recognition or rewards and I found a lot of the questions were leading in that direction. For me it's because of a passion, love, fanaticism and just the enjoyment of doing. Next comes the values, altruism, and community. But material rewards isn't something of interest. | Tom. Broughton | Europe
2020-04-17 20:54 | More than 3 years | WordPress | Values | Listing as a contributor on a project page | Front-End Development, UX Design, UI / Web Design, Feature Testing / QA, User Testing / Prototype testing | An hour or less a week
2020-04-19 03:27 | More than 3 years | The Linux kernel while it was under Linus Torvalds' complete control because he didn't care about anything but the quality of the code and if it wasn't "good enough" then he would tell you. It was the TRUEST form of OSS that I can think of. | Values | Swag (e.g. t-shirts, bags, pins), Listing as a contributor on a project page, being able to give back and help the projects that help me in my career so that the next generation can have the same opportunity |  | unfortunately I currently do not have any spare time to contribute to any additional projects | DO NOT let identity politics enter into any aspect of the project or it WILL fail. | William Penton | North America
2020-04-19 08:13 | More than 3 years |  | I am paid by my employer to contribute | Money |  | An hour or less a week
2020-04-19 09:06 | More than 3 years | Postgresql, it is an enabler | Values | Shout-out on social media (e.g. by a significant individual/organisation) | Kubernetes / New Relic / Infra management, Open Source and Open Development strategy, Backend | I have time and want to make sure you get it right! |  | christian chevalley | Asia
2020-04-19 10:56 | More than 3 years | Kubernetes | Fixing bugs | Swag (e.g. t-shirts, bags, pins), Shout-out on social media (e.g. by a significant individual/organisation), Digital credential (e.g. certificate or badge which you can share to evidence your contribution), Listing as a contributor on a project page, Prizes (e.g. a bug bounty) | Kubernetes / New Relic / Infra management | An hour or less a week |  |  | Europe
2020-04-19 11:30 | 1-3 years |  | Experience | Shout-out on social media (e.g. by a significant individual/organisation), Listing as a contributor on a project page | Front-End Development, React Development, Kubernetes / New Relic / Infra management | < 5 hours p/week |  | Federico | Europe
2020-04-19 16:33 | More than 3 years | Fedora | Experience | none of these. i wanted to learn. | Backend | 8 hours p/week |  |  | Europe
2020-04-19 17:56 | More than 3 years | WordPress, because it has been the one I've been most involved in | Values | Shout-out on social media (e.g. by a significant individual/organisation) |  |  | good luck! building community and being responsive is the key
2020-04-19 21:02 | More than 3 years | Jitsi - opensource videoconferencing | Social side | to help others solve problems | Kubernetes / New Relic / Infra management, Open Source and Open Development strategy | 8 hours p/week
2020-04-19 22:18 | More than 3 years | Apache Tika | Recognition | Shout-out on social media (e.g. by a significant individual/organisation), Digital credential (e.g. certificate or badge which you can share to evidence your contribution) | Kubernetes / New Relic / Infra management | < 5 hours p/week
2020-04-19 23:15 | 1-3 years | Ruby - 25 years old and still improving every year | Recognition | Swag (e.g. t-shirts, bags, pins) |  | None for this project |  |  | Australasia
2020-04-20 06:33 | More than 3 years | Apache | Values
2020-04-21 09:23 | More than 3 years | JRuby. Very friendly core team; high quality product | Creative outlet | Shout-out on social media (e.g. by a significant individual/organisation), Digital credential (e.g. certificate or badge which you can share to evidence your contribution), Listing as a contributor on a project page | Kubernetes / New Relic / Infra management, Feature Testing / QA | < 5 hours p/week |  |  | North America
2020-04-21 10:01 | 1-3 years | Linux for the countless forks; Symfony for the way they handle issues, labels, reusability,, news and thanks. | Scratching your own itch |  | Front-End Development, PHP Development, A/B Testing / Optimisation, User Testing / Prototype testing, User guides / technical documentation | I have time and want to make sure you get it right!
2020-04-21 13:25 | More than 3 years | Linux, Firefox | Values | Shout-out on social media (e.g. by a significant individual/organisation), Digital credential (e.g. certificate or badge which you can share to evidence your contribution), Listing as a contributor on a project page | Kubernetes / New Relic / Infra management, Feature Testing / QA | An hour or less a week |  | appzer0 | Europe
2020-04-21 15:16 | More than 3 years | WordPress. Because it's so successful. | Values | A belief in the concept | N/A | N/A | No thanks
2020-04-21 18:05 | More than 3 years | Not a single one, no. Firefox, Django, Python, node.js, Linux, too many to mention. | Values | Listing as a contributor on a project page | Front-End Development, PHP Development, UX Design, UI / Web Design, Feature Testing / QA, User guides / technical documentation | < 5 hours p/week |  |  | Europe
2020-04-23 07:04 | More than 3 years | Moodle | Values | Listing as a contributor on a project page | localization | An hour or less a week |  |  | Europe
2020-04-23 13:34 | 1-3 years | Mozilla Common Voice - applicable across a variety of contexts; solving a problem in digital inclusion. | Values | Swag (e.g. t-shirts, bags, pins), Shout-out on social media (e.g. by a significant individual/organisation), Digital credential (e.g. certificate or badge which you can share to evidence your contribution), Listing as a contributor on a project page | Engagement strategy / features | An hour or less a week |  |  | North America
2020-04-23 13:34 | More than 3 years | community | Values | Shout-out on social media (e.g. by a significant individual/organisation), Listing as a contributor on a project page | Front-End Development, React Development, Open Source and Open Development strategy, Engagement strategy / features, User Testing / Prototype testing, User guides / technical documentation | An hour or less a week
2020-04-24 21:29 | More than 3 years | DHIS2 - they became sustainable by working directly with Ministries of Health around the world, and have invested in helping public health field practitioners with little coding experience build new components. | It's a core part of my current job, but I don't necessarily do it to advance my career. |  | UX Design, Open Source and Open Development strategy, Engagement strategy / features, Feature Testing / QA, A/B Testing / Optimisation, User Testing / Prototype testing, User guides / technical documentation, other writing | An hour or less a week |  |  | North America
2020-04-28 10:11 | I've never contributed before |  | Experience | Prizes (e.g. a bug bounty) | UI / Web Design | An hour or less a week